Present: Richard Priestley, Julie Jones, Roger Hughes, Chris Gooding, Alastair Duncan

NOTES OF OUTCOME OF MD N’HOOD PLAN MEETING WITH DATA ORCHARD – 1 JULY 2015

Key points arising from the discussion included:

1. Add Loggerheads to area under discussion – 4500+population
2. Referendum to be carried out on all residents within designated area of NHP
3. Consultation process can be / should be wider / larger group of people than referendum
4. SC should bear cost of referendum
5. Set up informal consultation with those identified in 2 above for September 2015 by drop in event probably on Wednesday 9 September 2015 using market stall +FDC for detailed presentation to identify issues of concern to residents + evening event to catch others who cant attend in the daytime . to be based on potential desired actions in para “objectives and vision” in the Statement of intent +existing decisions e.g. SAMDEV
6. Need to adjust timetable ??? unclear at present
7. Need to action Business consultation at same time and go straight to questionnaire + organise Business breakfast to launch
8. Pack of questionnaires to be provided by DO for local adaptation and use
9. Freepost service for questionnaires to be paid for by MDTC and incorporated into consultation plans
10. ?? Questionnaire for young people aged 16+ ?? in conjunction with 6th form to be derived
11. Drayton Messenger to have copy for September edition by 1 August for 5 above
12. Drayton messenger to carry out formal public consultation in December with that edition to go out mid November
13. Chris Gooding – chris@dataorchard.co.uk telephone 07591 105912 to join Steering group
14. Next meeting of steering group to be held at 1000am on Wednesday 15 July 2015 at MD town hall

RJP July 2015 v2